## OVERVIEW
TOTAL BOM COST	$220.23

COMPONENT	SCHEMATIC ENTRY	PARTS SOURCING	FOOTPRINT ASSIGNMENT	MECHANICAL / PCB LAYOUT	CODE
CHASSIS	N/A	TODO	TODO	TODO	N/A
CABLES	TODO	TODO	TODO	TODO	N/A
AC PCA	INITIAL	PRELIMINARY	TODO	TODO	N/A
5V PWR PCA	INITIAL	PRELIMINARY	TODO	TODO	N/A
15V PWR PCA	INITIAL	PRELIMINARY	TODO	TODO	N/A
IO PCA	PRELIMINARY	PRELIMINARY	TODO	TODO	TODO
IO SELECT PCA	PRELIMINARY	PRELIMINARY	TODO	TODO	PRELIMINARY
MCU PCA	PRELIMINARY	PRELIMINARY	TODO	TODO	TODO
FRONT PANEL SELECT PCA	TODO	PRELIMINARY	TODO	TODO	TODO
ENCODER PCA	TODO	PRELIMINARY	TODO	TODO	TODO
FINAL ASSEMBLY HARDWARE	N/A	TODO	TODO	TODO	N/A
KNOB	N/A	PRELIMINARY	TODO	TODO	N/A
PWR SWITCH	PRELIMINARY	TODO	TODO	TODO	N/A
REMOTE	N/A	TODO	TODO	N/A	TODO

PROCESS STEPS
TODO	hasn’t been started yet
PRELIMINARY	In process of being done, not to first working draft status yet
INITIAL	draft, might be correct?
AWAITING REVIEW	inspect for completeness, correctness
CONFIRMED	has been reviewed, seems like it should work with other components.
PROTOTYPE	built, needs to be inspected to show it is working properly
TROUBLESHOOT	fix any issues found in proto
APPROVED	good to go
DONE	done

## MAIN ASSEMBLY
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
CHASSIS	1	$-	$-
CABLES	1	$-	$-
AC PCA	1	$5.48	$5.48
5V PWR PCA	1	$15.25	$15.25
15V PWR PCA	1	$26.73	$26.73
MAIN IO PCA	1	$71.88	$71.88
BALANCED IO PCA	1	$5.82	$5.82
IO SELECT PCA	1	$39.70	$39.70
MCU PCA	1	$6.53	$6.53
FRONT PANEL SELECT PCA	1	$16.12	$16.12
ENCODER PCA	2	$3.00	$6.00
GAIN STAGE PCA	1	$26.10	$26.10
HEADPHONE AMP PCA	1	$0.62	$0.62
FINAL ASSEMBLY HARDWARE	1		$-
KNOB	2		$-
PWR SWITCH	1		$-
REMOTE	1		$-

## CHASSIS
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
			$-

## CABLES
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
			$-

## AC PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
AC PCB	1		$-	N/A
CAP CER 0.1UF 1KV X7R 1812	1	$0.94	$0.94	C1	power switch bypass capacitor	DIGIKEY	399-9854-1-ND	https://www.digikey.com/product-detail/en/kemet/C1812C104KDRAC7800/399-9854-1-ND/3726199
RES SMD 4.7M OHM 1% 1/4W 1206	1	$0.10	$0.10	R1	bleedoff resistor	DIGIKEY	311-4.70MFRCT-ND	https://www.digikey.com/product-detail/en/yageo/RC1206FR-074M7L/311-4.70MFRCT-ND/731835
FUSE HLDR CARTRIDGE 250V 5A PCB	1	$0.62	$0.62	F1		DIGIKEY	36-4527-ND	https://www.digikey.com/product-detail/en/keystone-electronics/4527/36-4527-ND/8397
FUSE GLASS 500MA 220VAC 5X20MM	1	$2.38	$2.38	N/A	Installed in F1	DIGIKEY	486-1863-ND	https://www.digikey.com/products/en/circuit-protection/fuses/139?k=fuse&k=&pkeyword=fuse&sv=0&pv2088=u500mA&sf=1&FV=49%7C326748%2C69%7C355994%2C343%7C346273%2C1989%7C0%2C-8%7C139%2C46%7C13837&quantity=&ColumnSort=0&page=1&pageSize=25
TERM BLK 2POS TOP ENTRY 5MM PCB	3	$0.48	$1.44	J2, J3, J4	Connect to AC from EIC, supply to DC supplies in preamp (120V)	DIGIKEY	277-1592-ND	https://www.digikey.com/product-detail/en/phoenix-contact/1935310/277-1592-ND/568629

## 5V PWR PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
+5V PCB	1		$-	N/A
	1		$-	T2
BRIDGE RECT 1P 200V 1.5A 4DIP	1	$0.50	$0.50	D8		DIGIKEY	DF02M-ND	https://www.digikey.com/product-detail/en/on-semiconductor/DF02M/DF02M-ND/976938
FUSE HLDR CARTRIDGE 250V 5A PCB	1	$0.62	$0.62	F3		DIGIKEY	36-4527-ND	https://www.digikey.com/product-detail/en/keystone-electronics/4527/36-4527-ND/8397
FUSE GLASS 500MA 220VAC 5X20MM	1	$2.38	$2.38	N/A	Installed in F3	DIGIKEY	486-1863-ND	https://www.digikey.com/products/en/circuit-protection/fuses/139?k=fuse&k=&pkeyword=fuse&sv=0&pv2088=u500mA&sf=1&FV=49%7C326748%2C69%7C355994%2C343%7C346273%2C1989%7C0%2C-8%7C139%2C46%7C13837&quantity=&ColumnSort=0&page=1&pageSize=25
LED RED CLEAR 1206 SMD	1	$0.27	$0.27	D9	Power indicator LED	DIGIKEY	160-1167-1-ND	https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C150CKT/160-1167-1-ND/269239
RES SMD 430 OHM 1% 1/4W 1206	1	$0.07	$0.07	R8	Current set resistor for power indicator LED	DIGIKEY	311-430FRCT-ND	https://www.digikey.com/product-detail/en/yageo/RC1206FR-07430RL/311-430FRCT-ND/731861
TERM BLK 2POS TOP ENTRY 5MM PCB	1	$0.48	$0.48	J9		DIGIKEY	277-1592-ND	https://www.digikey.com/product-detail/en/phoenix-contact/1935310/277-1592-ND/568629
CONN HEADER VERT 2POS 2.5MM	3	0.131	$0.39	J10, J11, J12	5V OUTPUT	DIGIKEY	455-1611-ND	https://www.digikey.com/product-detail/en/jst-sales-america-inc/B2B-EH-A-LF-SN/455-1611-ND/926520
IC REG LINEAR 5V 1A TO220-3	1	1.54	$1.54	U1		DIGIKEY	296-47192-ND	https://www.digikey.com/product-detail/en/texas-instruments/LM7805CT-NOPB/296-47192-ND/3901929
RES 10 OHM 1W 1% AXIAL	1	$0.37	$0.37	R9		DIGIKEY	RSF1FT10R0CT-ND	https://www.digikey.com/product-detail/en/stackpole-electronics-inc/RSF1FT10R0/RSF1FT10R0CT-ND/6594481
CAP ALUM 2200UF 20% 35V RADIAL	2	$3.04	$6.08	C12, C13		DIGIKEY	493-4615-ND	https://www.digikey.com/products/en/capacitors/aluminum-electrolytic-capacitors/58?k=capacitor&k=&pkeyword=capacitor&sv=0&pv2049=u2200%C2%B5F&sf=0&FV=52%7C388275%2C69%7C411897%2C252%7C242904%2C405%7C316418%2C725%7C140003%2C725%7C140015%2C725%7C181967%2Cmu35V%7C2079%2C-8%7C58&quantity=&ColumnSort=0&page=1&pageSize=500
CAP CER 0.1UF 50V X7R 1206	2	$0.26	$0.52	C14, C15		DIGIKEY	311-1435-1-ND	https://www.digikey.com/product-detail/en/yageo/CC1206JRX7R9BB104/311-1435-1-ND/2833741
CAP ALUM 100UF 20% 35V RADIAL	1	$0.51	$0.51	C16		DIGIKEY	493-4662-1-ND	https://www.digikey.com/product-detail/en/nichicon/UKA1V101MED1TD/493-4662-1-ND/2787089
RES SMD 240 OHM 1% 1/4W 1206	1	$0.10	$0.10	R10		DIGIKEY	311-240FRCT-ND	https://www.digikey.com/products/en/resistors/chip-resistor-surface-mount/52?k=&pkeyword=&sv=0&pv7=2&pv3=1131&sf=0&FV=-6%7C5999%2C-8%7C52%2Cmu240+Ohms%7C2085&quantity=&ColumnSort=0&page=1&pageSize=500
TRIMMER 5K OHM 0.5W PC PIN TOP	1	$1.02	$1.02	RV3	Output voltage adjustment	DIGIKEY	3362P-502LF-ND	https://www.digikey.com/product-detail/en/bourns-inc/3362P-1-502LF/3362P-502LF-ND/1088421
DIODE GEN PURP 50V 1A SOD123FL	2	$0.20	$0.40	D10, D11		DIGIKEY	SM4001PL-TPMSCT-ND	https://www.digikey.com/product-detail/en/micro-commercial-co/SM4001PL-TP/SM4001PL-TPMSCT-ND/1793403

## 15V PWR PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
+/-15V PCB	1		$-	N/A
	1		$-	T1
BRIDGE RECT 1P 200V 1.5A 4DIP	1	$0.50	$0.50	D1		DIGIKEY	DF02M-ND	https://www.digikey.com/product-detail/en/on-semiconductor/DF02M/DF02M-ND/976938
FUSE HLDR CARTRIDGE 250V 5A PCB	1	$0.62	$0.62	F2		DIGIKEY	36-4527-ND	https://www.digikey.com/product-detail/en/keystone-electronics/4527/36-4527-ND/8397
FUSE GLASS 500MA 220VAC 5X20MM	1	$2.38	$2.38	N/A	Installed in F2	DIGIKEY	486-1863-ND	https://www.digikey.com/products/en/circuit-protection/fuses/139?k=fuse&k=&pkeyword=fuse&sv=0&pv2088=u500mA&sf=1&FV=49%7C326748%2C69%7C355994%2C343%7C346273%2C1989%7C0%2C-8%7C139%2C46%7C13837&quantity=&ColumnSort=0&page=1&pageSize=25
LED GREEN CLEAR 1206 SMD	2	$0.24	$0.48	D2, D3	Power indicator LEDs	DIGIKEY	160-1169-1-ND	https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C150GKT/160-1169-1-ND/269241
RES SMD 430 OHM 1% 1/4W 1206	2	$0.07	$0.14	R2, R3	Current set resistor for power indicator LEDs	DIGIKEY	311-430FRCT-ND	https://www.digikey.com/product-detail/en/yageo/RC1206FR-07430RL/311-430FRCT-ND/731861
CONN HEADER VERT 3POS 2.5MM	3	$0.48	$1.44	J6, J7, J8	+-15V OUTPUT	DIGIKEY	455-1612-ND	https://www.digikey.com/product-detail/en/jst-sales-america-inc/B3B-EH-A-LF-SN/455-1612-ND/926521
IC REG LINEAR 5V 1A TO220-3	1	1.54	$1.54	U1		DIGIKEY	296-47192-ND	https://www.digikey.com/product-detail/en/texas-instruments/LM7805CT-NOPB/296-47192-ND/3901929
IC REG LINEAR -5V 1.5A TO220-3	1	1.63	$1.63	U2		DIGIKEY	LM7905CTNS/NOPB-ND	https://www.digikey.com/product-detail/en/texas-instruments/LM7905CT-NOPB/LM7905CTNS-NOPB-ND/6349
RES 10 OHM 1W 1% AXIAL	2	$0.37	$0.74	R4, R5		DIGIKEY	RSF1FT10R0CT-ND	https://www.digikey.com/product-detail/en/stackpole-electronics-inc/RSF1FT10R0/RSF1FT10R0CT-ND/6594481
CAP ALUM 2200UF 20% 35V RADIAL	4	$3.04	$12.16	C2, C3, C4, C5		DIGIKEY	493-4615-ND	https://www.digikey.com/products/en/capacitors/aluminum-electrolytic-capacitors/58?k=capacitor&k=&pkeyword=capacitor&sv=0&pv2049=u2200%C2%B5F&sf=0&FV=52%7C388275%2C69%7C411897%2C252%7C242904%2C405%7C316418%2C725%7C140003%2C725%7C140015%2C725%7C181967%2Cmu35V%7C2079%2C-8%7C58&quantity=&ColumnSort=0&page=1&pageSize=500
DIODE GEN PURP 50V 1A SOD123FL	4	$0.20	$0.80	D4, D5, D6, D7		DIGIKEY	SM4001PL-TPMSCT-ND	https://www.digikey.com/product-detail/en/micro-commercial-co/SM4001PL-TP/SM4001PL-TPMSCT-ND/1793403
CAP ALUM 100UF 20% 35V RADIAL	2	$0.51	$1.02	C10, C11		DIGIKEY	493-4662-1-ND	https://www.digikey.com/product-detail/en/nichicon/UKA1V101MED1TD/493-4662-1-ND/2787089
CAP CER 0.1UF 50V X7R 1206	4	$0.26	$1.04	C6, C7, C8, C9		DIGIKEY	311-1435-1-ND	https://www.digikey.com/product-detail/en/yageo/CC1206JRX7R9BB104/311-1435-1-ND/2833741
RES SMD 240 OHM 1% 1/4W 1206	2	$0.10	$0.20	R6, R7		DIGIKEY	311-240FRCT-ND	https://www.digikey.com/products/en/resistors/chip-resistor-surface-mount/52?k=&pkeyword=&sv=0&pv7=2&pv3=1131&sf=0&FV=-6%7C5999%2C-8%7C52%2Cmu240+Ohms%7C2085&quantity=&ColumnSort=0&page=1&pageSize=500
TRIMMER 5K OHM 0.5W PC PIN TOP	2	$1.02	$2.04	RV1, RV2	Output voltage adjustment	DIGIKEY	3362P-502LF-ND	https://www.digikey.com/product-detail/en/bourns-inc/3362P-1-502LF/3362P-502LF-ND/1088421

## MAIN IO PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
MAIN IO PCB	1		$-	N/A
RCA JACK PC MOUNT WHITE	6	$5.99	$35.94		Most likely a knockoff, I don’t care.	GOOD COMPONENT	CMC 805-2.5F-G	https://www.goodcomponent.com/products/connectors-switches/rca-connector/cmc-805-25f-g-gold-plated-brass-female-rca-jack-connector-whitered-cmc-805-25f-g-855.html
RCA JACK PC MOUNT RED	6	$5.99	$35.94		Most likely a knockoff, I don’t care.	GOOD COMPONENT	CMC 805-2.5F-G	https://www.goodcomponent.com/products/connectors-switches/rca-connector/cmc-805-25f-g-gold-plated-brass-female-rca-jack-connector-whitered-cmc-805-25f-g-855.html

## BALANCED IO PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
BALANCED IO PCB	1		$-	N/A
XLR FEMALE	2	$0.92	$1.84			MOUSER	568-NC3FAAV-1	https://www.mouser.com/ProductDetail/Neutrik/NC3FAAV1?qs=sGAEpiMZZMv0W4pxf2HiV%252Bb1wOKdn1J5TSLePT2Zr6I%3D
XLR MALE	2	$0.77	$1.54			MOUSER	568-NC3MAAV-1	https://www.mouser.com/ProductDetail/Neutrik/NC3MAAV-1?qs=3hqMSz60ubQNQZ6GY809OQ%3D%3D
LED GREEN CLEAR 1206 SMD	2	$0.24	$0.48	D14, D15	Power indicator LEDs	DIGIKEY	160-1169-1-ND	https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C150GKT/160-1169-1-ND/269241
RES SMD 430 OHM 1% 1/4W 1206	2	$0.07	$0.14	R19, R24	Current set resistor for power indicator LEDs	DIGIKEY	311-430FRCT-ND	https://www.digikey.com/product-detail/en/yageo/RC1206FR-07430RL/311-430FRCT-ND/731861
IC OPAMP JFET 2 CIRCUIT 8DIP	3	0.607	$1.82	U6, U7, U8	Any dual op amp that fits TL072 Pinout	DIGIKEY	296-14997-5-ND	https://www.digikey.com/product-detail/en/texas-instruments/TL072IP/296-14997-5-ND/563039

## IO SELECT PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
IO SELECT PCB	1		$-	N/A
IC I/O EXPANDER SPI 16B 28SDIP	1	$1.26	$1.26	U9		DIGIKEY	MCP23S17-E/SP-ND	https://www.digikey.com/product-detail/en/microchip-technology/MCP23S17-E-SP/MCP23S17-E-SP-ND/894276
IC PWR RELAY 7NPN 1:1 16SO	2	$0.59	$1.18	U10, U11		DIGIKEY	ULN2003ADR2GOSCT-ND	https://www.digikey.com/product-detail/en/on-semiconductor/ULN2003ADR2G/ULN2003ADR2GOSCT-ND/2623488
RELAY TELECOM DPDT 1A 5VDC	7	$4.69	$32.83	K1, K2, K3, K4, K5, K6, K7		DIGIKEY	Z2144-ND	https://www.digikey.com/product-detail/en/omron-electronics-inc-emc-div/G6JU-2P-Y-DC5/Z2144-ND/699971
RES SMD 430 OHM 1% 1/4W 1206	1	$0.07	$0.07	R43	Current set resistor for power indicator LED	DIGIKEY	311-430FRCT-ND	https://www.digikey.com/product-detail/en/yageo/RC1206FR-07430RL/311-430FRCT-ND/731861
LED RED CLEAR 1206 SMD	1	$0.27	$0.27	D16	Power indicator LED	DIGIKEY	160-1167-1-ND	https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C150CKT/160-1167-1-ND/269239
CONN HEADER VERT 2POS 2.54MM	1	$0.06	$0.06	J62		DIGIKEY	952-2262-ND	https://www.digikey.com/product-detail/en/harwin-inc/M20-9990246/952-2262-ND/3728226
CONN RCPT 2POS 0.1 TIN PCB	1	$0.66	$0.66	J61		DIGIKEY	952-1776-ND	https://www.digikey.com/product-detail/en/harwin-inc/M20-7820246/952-1776-ND/3727745
CONN HEADER VERT 3POS 2.54MM	6	$0.14	$0.82	J52, J53, J54, J55, J58, J59		DIGIKEY	952-2264-ND	https://www.digikey.com/product-detail/en/harwin-inc/M20-9990346/952-2264-ND/3728228
CONN RCPT 3POS 0.1 TIN PCB	4	$0.64	$2.55	J51, J60, J63, J64		DIGIKEY	952-1784-ND	https://www.digikey.com/product-detail/en/harwin-inc/M20-7820346/952-1784-ND/3727753

## GAIN STAGE PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
GAIN STAGE PCB	1		$-	N/A
RES SMD 430 OHM 1% 1/4W 1206	2	$0.07	$0.14	R82, R83, R86	Current set resistor for power indicator LEDs	DIGIKEY	311-430FRCT-ND	https://www.digikey.com/product-detail/en/yageo/RC1206FR-07430RL/311-430FRCT-ND/731861
LED GREEN CLEAR 1206 SMD	2	$0.24	$0.48	D17, D18	Power indicator LEDs	DIGIKEY	160-1169-1-ND	https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C150GKT/160-1169-1-ND/269241
LED RED CLEAR 1206 SMD	1	$0.27	$0.27	D21	Power indicator LED	DIGIKEY	160-1167-1-ND	https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C150CKT/160-1167-1-ND/269239
IC DAC 8BIT V-OUT 14SOIC	2	1.29	$2.58	U12, U13	DAC to set gain	DIGIKEY	MCP4902-E/SL-ND	https://www.digikey.com/product-detail/en/microchip-technology/MCP4902-E-SL/MCP4902-E-SL-ND/2332822
IC OPAMP JFET 2 CIRCUIT 8DIP	4	0.607	$2.43	U14, U15, U18, U21	Any dual op amp that fits TL072 Pinout	DIGIKEY	296-14997-5-ND	https://www.digikey.com/product-detail/en/texas-instruments/TL072IP/296-14997-5-ND/563039
Audio Amplifiers Trimmable VCA .02% THD	4	5.05	$20.20	U16, U17, U19, U20	Sets gain of preamp, ctrl voltage supplied from MCP4902	MOUSER	887-2181CS08-U	https://www.mouser.com/ProductDetail/THAT/2181CS08-U?qs=sGAEpiMZZMtxdzBvM0rKcQBFpLukO3I7ryY%2FmA%252BZ4ws%3D

## MCU PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
MCU PCB	1		$-	N/A
ESP32 MCU	1	$6.53	$6.53			AMAZON		https://www.amazon.com/gp/product/B07Q576VWZ/ref=ppx_yo_dt_b_asin_title_o02_s01?ie=UTF8&psc=1

## FRONT PANEL SELECT PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
FRONT PANEL PCB	1		$-	N/A
MULTIPLE SWITCH DETECTION INTERFACE	1	$4.19	$4.19		condenses up to 22 input switches to SPI and flag line	DIGIKEY	MC33978AEK-ND	https://www.digikey.com/product-detail/en/nxp-usa-inc/MC33978AEK/MC33978AEK-ND/5451804
CAPACITIVE TOUCH SWITCH MOMENTARY	6	$0.74	$4.43			AMAZON	3-01-0019	https://www.amazon.com/gp/product/B00HFQEFWQ/ref=ppx_yo_dt_b_asin_title_o02_s04?ie=UTF8&psc=1
NEOPIXEL RGB LED	15	0.5	$7.50			DIGIKEY	1568-1800-ND	https://www.digikey.com/product-detail/en/sparkfun-electronics/COM-11821/1568-1800-ND/6163706
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-
			$-

## HEADPHONE AMP PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
HEADPHONE AMP PCB	1		$-	N/A
LED GREEN CLEAR 1206 SMD	2	$0.24	$0.48	D19, D20	Power indicator LEDs	DIGIKEY	160-1169-1-ND	https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C150GKT/160-1169-1-ND/269241
RES SMD 430 OHM 1% 1/4W 1206	2	$0.07	$0.14	R84, R85	Current set resistor for power indicator LEDs	DIGIKEY	311-430FRCT-ND	https://www.digikey.com/product-detail/en/yageo/RC1206FR-07430RL/311-430FRCT-ND/731861

## ENCODER PCA
DESCRIPTION	QTY	UNIT PRICE	LINE PRICE	REF DES	NOTE	SUPPLIER	SUPPLIER PN	LINK
ENCODER PCB	1		$-	N/A
ROTARY ENCODER	2	$1.50	$3.00			AMAZON		https://www.amazon.com/WGCD-KY-040-Degree-Encoder-Arduino/dp/B07B68H6R8/ref=sr_1_2_sspa?keywords=rotary+encoder&qid=1576638369&sr=8-2-spons&psc=1&spLa=ZW5jcnlwdGVkUXVhbGlmaWVyPUFVTFVKVEkzV0s0OVMmZW5jcnlwdGVkSWQ9QTA4MTU4ODAyRDNNREtKTTAwUzlQJmVuY3J5cHRlZEFkSWQ9QTA4MTA3MDMzT1k0N01TUzc3Nzc4JndpZGdldE5hbWU9c3BfYXRmJmFjdGlvbj1jbGlja1JlZGlyZWN0JmRvTm90TG9nQ2xpY2s9dHJ1ZQ==

## KNOBS
https://www.aliexpress.com/item/32826735571.html?spm=a2g0o.detail.1000014.49.552633ddMk7jmK&gps-id=pcDetailBottomMoreOtherSeller&scm=1007.13338.146400.0&scm_id=1007.13338.146400.0&scm-url=1007.13338.146400.0&pvid=77d585b8-cfe3-496e-b5c0-a8b348c09917
https://www.aliexpress.com/item/32800269274.html?spm=a2g0o.detail.1000014.47.2e335ab8OaO0uM&gps-id=pcDetailBottomMoreOtherSeller&scm=1007.13338.146400.0&scm_id=1007.13338.146400.0&scm-url=1007.13338.146400.0&pvid=b5d39abb-c096-4304-b092-21aac124110e
https://www.aliexpress.com/item/32953404871.html?spm=a2g0o.detail.1000014.15.37682360CE9EJG&gps-id=pcDetailBottomMoreOtherSeller&scm=1007.13338.146400.0&scm_id=1007.13338.146400.0&scm-url=1007.13338.146400.0&pvid=a4698c2a-8748-4ab6-ac4f-2635c043b623
https://www.aliexpress.com/item/32627105289.html?spm=a2g0o.detail.1000014.45.1ba122e6zNLaBl&gps-id=pcDetailBottomMoreOtherSeller&scm=1007.13338.146400.0&scm_id=1007.13338.146400.0&scm-url=1007.13338.146400.0&pvid=2492ee03-5f0d-4d4a-88eb-1d050fc62d22